## Gantt chart - examples
Gantt chart in Excel
The workbook shows two examples of Gantt chart in Excel.
| Author | Ablebits.com
| Last update | 2020-11-24
| Tutorial URL | How to make a Gantt chart in Excel
Examples:
• | Gantt chart - example 1
• | Gantt chart - example 2

## Gantt chart1
Task | Start Date | End Date | Duration
Gather requirements | 2014-04-01 | 2014-04-06 | 5
UI Design | 2014-04-07 | 2014-04-18 | 11
Coding | 2014-04-19 | 2014-05-11 | 22
Unit tests | 2014-05-12 | 2014-05-18 | 6
System test | 2014-05-19 | 2014-05-30 | 11
Beta 1 | 2014-05-31 | 2014-06-02 | 2
Bug fixes | 2014-06-03 | 2014-06-17 | 14
Improvements | 2014-06-18 | 2014-07-02 | 14
Final testing | 2014-07-03 | 2014-07-09 | 6
Release version | 2014-07-10 | 2014-07-12 | 2
Formulas:
End Date = [Start Date]+5
Start Date = [End Date, row above]+1

## Gantt chart2
Task | Start Date | End Date | Duration
Task 1 | 2014-04-01 | 2014-05-31 | 60
Task 2 | 2014-06-01 | 2014-08-05 | 65
Task 3 | 2014-08-06 | 2014-08-28 | 22
Task 4 | 2014-08-29 | 2014-10-14 | 46
Task 5 | 2014-10-15 | 2014-10-26 | 11
Task 6 | 2014-10-27 | 2014-12-06 | 40
Formulas:
End Date = [Start Date]+60
Start Date = [End Date, row above]+1